## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-ID | Enterprise Email Intelligence Study & Use Case Analysis | MUST HAVE | No Dependency | Entire Team | 3- Completed
Sprint 2 | Sprint 2 | US-ID | Dataset Collection (Emails & Documents) and Preprocessing | MUST HAVE | No Dependency | Entire Team | 3- Completed
Sprint 3 | Sprint 3 | US-ID | Text Chunking Strategy & Embedding Model Selection | MUST HAVE | Lucidchart | Entire Team | 3- Completed
Sprint 4 | Sprint 4 | US-ID | Vector Database Setup (ChromaDB Integration) | MUST HAVE | Lucidchart | Entire Team | 3- Completed
Sprint 5 | Sprint 5 | US-ID | LangChain RAG Pipeline Implementation | MUST HAVE | ChromaDB | Entire Team | 3- Completed
Sprint 6 | Sprint 6 | US-ID | Semantic Search & Context Retrieval Development | MUST HAVE | OpenAI Embeddings, ChromaDB | Entire Team | 3- Completed
Sprint 7 | Sprint 7 | US-ID | LLM Integration for Intelligent Q&A and Summarization | MUST HAVE | LangChain, ChromaDB, Python Modules | Entire Team | 3- Completed
Sprint 8 | Sprint 8 | US-ID | Backend Development using FastAPI | MUST HAVE | FastAPI, LangChain | Entire Team | 3- Completed
Sprint 9 | Sprint 9 | US-ID | Frontend Dashboard Development (Streamlit) | MUST HAVE | Streamlit, Backend APIs | Entire Team | 3- Completed
Sprint 10 | Sprint 10 | US-ID | System Integration (Frontend + Backend + Vector DB) | MUST HAVE | All Previous Modules | Entire Team | 3- Completed
Sprint 11 | Sprint 11 | US-ID | Performance Optimization & Testing | MUST HAVE | Entire System | Entire Team | 3- Completed
Sprint 12 | Sprint 12 | US-ID | Deployment, Documentation & Final Demo Preparation | MUST HAVE | Completed System | Entire Team | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 83 | 33 | 27 | 20 | 18 | 16 | 13 | 10 | 5 | 4 | 2 | 1 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-ID | 1 | Enterprise Email Intelligence Study & Use Case Analysis | 31/12/2025 | 2026-01-01 | Entire Team | Others | 3- Completed | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-ID | 2 | Dataset Collection (Emails & Documents) and Preprocessing | 2006-01-05 | 2026-01-09 | Mann & Monish | Design | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-ID | 3 | Text Chunking Strategy & Embedding Model Selection | 2026-10-01 | 16/01/2026 | Mann | Design | 3- Completed | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-ID | 4 | Vector Database Setup (ChromaDB Integration) | 17/01/2026 | 19/01/2026 | Mann | Design | 3- Completed | 4 | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-ID | 5 | LangChain RAG Pipeline Implementation | 20/01/2026 | 25/01/2026 | Mann & Mahesh | Build | 3- Completed | 6 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-ID | 6 | Semantic Search & Context Retrieval Development | 26/01/2026 | 31/01/2026 | Mann & Mandara | Build | 3- Completed | 7 | 4 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0
US-ID | 7 | LLM Integration for Intelligent Q&A and Summarization | 2026-02-02 | 2026-07-02 | 2- Mann | Build | 3- Completed | 10 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
US-ID | 8 | Backend Development using FastAPI | 2026-08-02 | 2026-11-02 | 2- Mann | Build | 3- Completed | 9 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-ID | 9 | Frontend Dashboard Development (Streamlit) | 2026-12-02 | 14/02/2026 | Mann & Mandara | Build | 3- Completed | 8 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0
US-ID | 10 | System Integration (Frontend + Backend + Vector DB) | 15/02/2026 | 17/02/2026 | 3- Completed | Build | 3- Completed | 9 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-ID | 11 | Performance Optimization & Testing | 18/02/2026 | 20/02/2026 | Entire Team | Build | 3- Completed | 10 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-ID | 12 | Deployment, Documentation & Final Demo Preparation | 21/02/2026 | 23/02/2026 | Entire Team | Test | 3- Completed | 15 | 4 | 4 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Confusion in designing RAG-based system architecture and module interaction | Conducted team discussion and finalized clear RAG pipeline with defined modules
Sprint 2 | Day 5 | Difficulty in preprocessing unstructured email and document formats | Implemented structured cleaning pipeline and standardized document formatting
Sprint 3 | Day 10 | Uncertainty in selecting optimal chunk size and embedding configuration | Tested multiple chunk sizes and overlap strategies to optimize retrieval accuracy
Sprint 4 | Day 15 | Issues while configuring ChromaDB collections and metadata schema | Redesigned metadata structure and validated embedding storage process
Sprint 5 | Day 20 | Low similarity accuracy in semantic search results | Tuned similarity thresholds and improved retrieval parameters in LangChain
Sprint 6 | Day 26 | Inconsistent LLM responses due to prompt design limitations | Refined prompt templates and improved context injection from retrieved documents
Sprint 7 | Day 32 | API latency and async handling issues in FastAPI backend | Optimized async endpoints and improved connection handling
Sprint 8 | Day 38 | Frontend and backend integration mismatch in Streamlit API calls | Debugged API routes and ensured consistent request-response format
Sprint 9 | Day 44 | Performance drop when handling larger email datasets | Implemented batching and optimized embedding retrieval
Sprint 10 | Day 48 | Response delay due to inefficient similarity search parameters | Adjusted scoring threshold and added caching mechanism
Sprint 11 | Day 52 | Minor bugs identified during system-wide integration testing | Performed regression testing and added structured error handling
Sprint 12 | Day 55 | Final demo instability and deployment configuration issues | Conducted final validation testing and stabilized deployment setup

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 31/12/2025 | 2026-01-01 | Entire Team | Requirement analysis and system architecture finalization for Enterprise Email Intelligence | Initial scope clarity | Conducted discussions and defined RAG workflow | Finalized system modules and roadmap
2 | Sprint 2 | 2026-05-01 | 2026-09-01 | Mann & Monish | Dataset preparation and email/document preprocessing | Handling unstructured email formats | Standardized cleaning and formatting pipeline | Prepared structured dataset for embeddings
3 | Sprint 3 | 2026-10-01 | 16/01/2026 | Mann | Text chunking and embedding model integration | Chunk size optimization | Tested multiple chunk sizes and overlaps | Optimized embeddings generated
4 | Sprint 4 | 17/01/2026 | 19/01/2026 | Mann | ChromaDB setup and vector collection configuration | Metadata structuring | Designed schema with document IDs and tags | Functional vector database created
5 | Sprint 5 | 20/01/2026 | 25/01/2026 | Mann & Mahesh | LangChain RAG pipeline development | Retrieval accuracy | Configured similarity search and retrieval chain | Working semantic search system
6 | Sprint 6 | 26/01/2026 | 31/01/2026 | Mann & Mandara | LLM integration for Q&A and summarization | Response consistency | Tuned prompts and retrieval depth | Context-aware intelligent responses generated
7 | Sprint 7 | 2026-02-02 | 2026-07-02 | Mann | FastAPI backend development | API response latency | Optimized async query handling | Stable backend APIs deployed locally
8 | Sprint 8 | 2026-08-02 | 2026-11-02 | Mann | Streamlit frontend dashboard development | UI responsiveness | Structured modular UI components | Functional enterprise dashboard built
9 | Sprint 9 | 2026-12-02 | 14/02/2026 | Mann & Mandara | Backend and frontend integration | API synchronization | Tested complete query-response flow | End-to-end system working
10 | Sprint 10 | 15/02/2026 | 17/02/2026 | Mann | Performance optimization and retrieval tuning | Similarity threshold refinement | Adjusted scoring and caching | Improved accuracy and response time
11 | Sprint 11 | 18/02/2026 | 20/02/2026 | Entire Team | Full system testing and debugging | Minor integration issues | Conducted regression testing | Stable demo-ready system
12 | Sprint 12 | 21/02/2026 | 23/02/2026 | Entire Team | Documentation, deployment setup, and demo preparation | Presentation clarity | Prepared architecture diagrams and demo script | Final project submission completed